## Phase 2 Progress
AxiaOps Phase 2 (Alpha) — Task Tracking ¦ Updated: April 12, 2026 — 11:30 AM
Updated: April 12, 2026
Task | Status | Started | Target | Priority | Implemented slog/Sentry/Prometheus ¦ Tests: logging_test.go (output formats, log levels) | Owner | Dependencies
✅ Observability (Structured logging,, Prometheus) | DONE | Apr 7 | Apr 10 | P0 | All /v1/ routes, nginx proxy configured ¦ Tests: handler_test.go (/v1/ prefix verification) | Ahmed | —
✅ Versioned Migrations | DONE | Apr 9 | Apr 10 | P0 | 1. Add golang-migrate CLI + Go module dependency 2. Create 001_initial.sql (baseline schema) and 002_add_tenant_id.sql (RLS policies) 3. Wire the migration runner into both api and ingestion startup using MIGRATION_DATABASE_URL 4. Remove inline CREATE TABLE IF NOT EXISTS / ALTER TABLE calls from application code 5. Verify with make test-postgres that schema_migrations table is populated
✅ API Versioning (/v1/ prefix) | DONE | Apr 8 | Apr 10 | P0 | Per-tenant sliding window, 60 req/min ¦ Tests: ratelimit_test.go (isolation, token bucket, concurrent access) | Ahmed | —
✅ Graceful Shutdown (SIGTERM handling) | ✅ DONE | Apr 9 | Apr 10 | P0 | signal.NotifyContext + server.Shutdown() in API & ingestion services. 30-sec timeout, request draining, DB cleanup. Test: make test-shutdown | Ahmed | —
✅ Graceful Shutdown (SIGTERM handling) | ✅ DONE | Apr 9 | Apr 10 | P0 | Both API and ingestion need signal.NotifyContext + server.Shutdown() | Ahmed | —
✅ GitLab CI Pipeline (build + deploy stages) | ✅ DONE | Apr 5 | Apr 12 | P0 | Currently only test stage; need Docker build, ECR push, App Runner deploy | Ahmed | API versioning
❌ Scheduled Auto-Scan (24h interval per account) | NOT STARTED | — | May 15 | P1 | Background ticker in API; respects scan_interval_hours field; skips if already scanning | Ahmed | Graceful shutdown
❌ cost_records Retention (90-day cleanup) | NOT STARTED | — | May 20 | P1 | Daily cleanup job; DELETE old records; add created_at index | Ahmed | Scheduled auto-scan
✅ Scan Recovery (Stuck scan timeout) | DONE | Apr 9 | Apr 12 | P1 | Startup recovery + 5-min ticker exist; 15-min stuck timeout implemented | Ahmed | Rate limiting
❌ Redis Integration (JWKS cache, scan queue, rate limiting) | NOT STARTED | — | June 1 | P1 | Dev: container in docker-compose; Production: ElastiCache Serverless | Ahmed | Graceful shutdown
❌ Weekly Email Digest + Slack Alerts | NOT STARTED | — | June 15 | P2 | Email: Resend or SendGrid; Slack webhook; daily digest of ghost spend | Ahmed | Redis integration
❌ Production Deployment (App Runner, RDS, Terraform) | NOT STARTED | — | July 1 | P0 | App Runner for API + ingestion; RDS PostgreSQL db.t4g.micro; Secrets Manager | Ahmed | All Phase 2 items
Summary
Status Distribution:
✅ Done: | 7
🔄 In Progress: | 0
⏸ Blocked/Not Started: | 5
Phase 2 Timeline
May 2026: Core infrastructure (graceful shutdown, CI/CD, scheduled scans, cost cleanup)
June 2026: Redis integration, alerting (email + Slack)
July 2026: Production deployment to App Runner + RDS
NEXT STEPS & DEPENDENCIES
🎯 PRIORITY: Graceful Shutdown (P0, May 1 target)
Blocker for: Scheduled Auto-Scan, Redis Integration, Production Deployment
🔧 GRACEFUL SHUTDOWN IMPLEMENTATION
API Service (services/api/cmd/main.go, lines 200-243):
✓ signal.NotifyContext(shutdownCtx, os.Interrupt, syscall.SIGTERM)
✓ server.Shutdown(shutdownCtx) with 30-second timeout
✓ Request draining, database cleanup, logging
Ingestion Service (services/ingestion/cmd/main.go, lines 167-210):
✓ Same pattern: signal.NotifyContext + server.Shutdown()
✓ Handles both SIGTERM (App Runner) and SIGINT (Ctrl+C)
📝 Test Command: make test-shutdown